To: DG/DDG (TO)/Acting Director (Space)

From: B.S. Marasinghe

Date: 02.04.2025

Project Proposal

- Project Title: Field-Based Flood Inundation Mapping Using Digital Elevation Data for Floodplain Identification in the Kandy District

- Action Plan Code:

Project Code: 2026/STA/PUB/KFIM

- Background/ Introduction:

27 November 2025, Sri Lanka was significantly affected by the impact of Cyclone Ditwa, which triggered widespread flooding across the country. According to United Nations situation reports, nearly one-fifth of the national land area was inundated or directly affected by floodwaters. The event represented one of the most extensive flood situations in recent decades and highlighted the vulnerability of many settlements located within riverine low-lying areas.

In the Kandy region, including Gampola and surrounding areas, this flood event occurred after approximately four decades without a comparable large-scale inundation. As a result, many communities and local authorities lacked clearly identified and publicly understood floodplain boundaries. Although floodplain relocation and risk reduction measures have been discussed at policy level in the past, implementation has been limited due to the absence of scientifically validated and spatially defined floodplain maps.

Furthermore, during the peak of the event, suitable cloud-free satellite imagery, particularly Sentinel optical data, was not available for the Kandy region. This significantly limited the ability to map flood inundation using conventional satellite-based approaches. In such conditions, alternative methods that integrate field verification and elevation analysis become essential for reliable flood assessment.

To address this gap, an integrated field-verified and satellite elevation–based flood inundation map was developed for the Gampola area. The process involved road-by-road field visits, direct engagement with affected communities to identify maximum flood water reach (flood zero-level), and extraction of elevation data from ALOS digital elevation models to define inundation boundaries. This approach allowed flood extent delineation even in the absence of suitable real-time satellite imagery.

However, validation has so far been limited to the Gampola section. There remains a critical need to extend systematic field verification and boundary refinement to the remaining affected regions in order to ensure scientific reliability, administrative usability, and long-term floodplain delineation.

Identifying floodplain boundaries is not only important for documenting past flood events but is essential for disaster risk reduction, land-use planning, infrastructure development control, and informed relocation decisions. The recent flood event presents a rare and valuable opportunity to scientifically define flood-prone areas based on real observations before future development increases exposure and vulnerability.

- Objectives 	:

- To develop and operationalize a mobile-based application for GPS-referenced flood data collection.

- To establish coordination with Divisional Secretariat and Grama Niladhari (GN) officers for structured field validation within selected flood-affected areas.

- To conduct systematic field verification and collect GPS-referenced flood level observations beyond the previously validated Gampola region.

- To integrate field-verified flood data with ALOS Digital Elevation Model (DEM) data using ArcGIS for refinement of inundation boundaries.

- To delineate floodplain areas and produce validated flood inundation and floodplain maps for the Kandy District.

- Expected output/ outcome:

Outputs

The proposed project is expected to generate scientifically validated flood inundation maps for the Kandy District through systematic field verification integrated with ALOS digital elevation analysis. The refinement of flood boundaries based on observed flood levels will significantly improve the spatial accuracy and administrative reliability of flood extent mapping.

The validated flood inundation maps and delineated floodplain zones will primarily support district-level disaster risk reduction, land-use planning, settlement management, and infrastructure development control. By clearly identifying areas vulnerable to similar magnitude flood events, the project will provide evidence-based spatial information to guide future planning and risk-informed decision-making.

In addition to these administrative and planning benefits, the delineated floodplain maps will serve as a valuable scientific baseline for future research. The identified flood-affected zones can support studies in soil science, hydrology, geomorphology, sediment transport, and environmental change. The project will also produce a GPS-referenced flood verification dataset that may be used in future hydrological modelling and comparative flood studies. Final outputs and technical documentation will be disseminated to relevant authorities and research institutions to ensure both practical application and long-term scientific value.

Outcomes:

- Validated flood inundation map and floodplain delineation map for the Kandy District, based on systematic field verification and elevation-based analysis.

- Operational mobile-based flood data collection application, enabling structured and GPS-referenced field validation for future flood events.

- Scientifically validated spatial dataset, supporting future geological, soil science, hydrological, and environmental research

- KPIs with KPI targets:

No of flood inundation maps

No. of technical papers published

- Methodology:

The proposed study will employ an integrated field-based and elevation-based mapping approach to validate and refine flood inundation boundaries within the Kandy District. The primary spatial dataset used in this study will be the ALOS Digital Elevation Model (DEM), which provides elevation information suitable for terrain-based flood analysis. Spatial analysis, data integration, and map production will be carried out using ArcGIS software. In addition, a simple mobile-based data collection application will be developed to standardize field data acquisition and ensure spatial accuracy.

Institutional Coordination and Digital Tool Development

The first stage of the methodology will focus on institutional coordination and preparation for field validation. Formal communication will be established with Divisional Secretariat offices and Grama Niladhari (GN) officers within selected flood-affected areas of the Kandy District. The objectives of the project and the required support for field verification will be clearly communicated to ensure administrative collaboration. At this stage, the mobile data collection application will be developed to enable the recording of GPS-referenced flood level observations, photographic documentation, and descriptive field notes in a structured and standardized format.

Field Verification and Data Collection

Following preparatory coordination, structured field verification will be conducted across flood-affected areas beyond the already validated Gampola region. Field teams, in collaboration with GN officers and affected communities, will identify the maximum observed flood water levels and record flood zero-level locations using GPS-enabled mobile devices. Road-by-road verification will be conducted where necessary to confirm inundation limits and ensure consistency with community-reported flood boundaries.

Flood Inundation Boundary Refinement

The collected field data will then be integrated with the ALOS DEM within the ArcGIS environment. Elevation values corresponding to verified flood levels will be analyzed to refine and adjust the previously generated flood inundation boundaries. Spatial consistency, topographic continuity, and hydrological plausibility will be assessed to produce an updated and validated flood inundation map for the Kandy District.

Floodplain Delineation and Dissemination

Based on the refined inundation extents, potential floodplain zones will be delineated through elevation-based spatial analysis and interpretation. The final outputs will include validated flood inundation maps and preliminary floodplain delineation maps, which will be disseminated to relevant district-level and disaster management authorities to support land-use planning, environmental assessment, and disaster risk reduction initiatives.

- Project Timeline

Date of Commencement: 2026-03-01

Duration of the Project (in months):  4 months

- Project Team:

Project Manager:

Sampath Marasinghe (SM)	   - Senior Research Scientist

Internal Staff:

Mohamed Rila (MR)	 - Research Scientist

Nilushika (NJ)      	 - Research Scientist

Mahesh Chathuranga (MC)    - Research Scientist

Manuja Priyadarshana (MP) - Software Engineer

- Activity Schedule with Staff Allocation:

| Activity | Month/Year 2026 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Jan | Feb | Mar | Apr | June | July | Responsibility & Man Months |
| Development and Testing of Mobile-Based Flood Data Collection |  |  |  |  |  |  | MP-1 |
| Institutional Coordination and Administrative Communication (Divisional Secretariat and GN Officers) |  |  |  |  |  |  | SM -0.5 MR-0.5 NJ-0.5 |
| Preparation of Base Spatial Data |  |  |  |  |  |  | SM-0.5 MC-0.5 |
| Field Verification Planning and Logistics Arrangement |  |  |  |  |  |  | MR-1 SM-0.5 |
| Systematic Field Survey and GPS-Based Flood Data Collection |  |  |  |  |  |  | SM-1 MC-0.5 MR-0.5 |
| Integration of Field Data and Preparation of Validated Flood Inundation |  |  |  |  |  |  | SM -0.5 MC-0.5 NJ-0.5 |
| Technical Documentation and Dissemination of Final Outputs Deforestation Estimation |  |  |  |  |  |  | SM-0.5 MC-0.5 MR -0.5 NJ -0.5 |
| Total |  |  |  |  |  |  | Sc. Months- SM- 3.5 MR – 2.5 MC – 2 NJ – 1.5 MP-1 |

- Major Equipment/ Software Required:

High Speed workstation computer – already available

Required RS/GIS software             – already available

Satellite data                                  – freely downloadable

- Estimated Capital Expenditure:

- Estimated Recurrent Expenditure (excluding staff costs) : Rs 500,000.00

(See Annexure 1 for detailed recurrent expenditure)

- External funding:   No

- User Beneficiary:

The primary beneficiaries of this project will be district-level administrative and technical authorities within the Kandy District, particularly the District Secretariat and Divisional Secretariats, for evidence-based flood risk management and land-use planning.

Technical and operational agencies such as the Disaster Management Centre (DMC), Mahaweli Authority of Sri Lanka, and relevant water resource management institutions will benefit from scientifically validated flood inundation and floodplain maps to support flood mitigation and watershed management activities.

In addition, academic and professional bodies including the Soil Science Society of Sri Lanka, hydrological research institutions, and environmental authorities will benefit from the validated spatial dataset for future soil, hydrological, and environmental research.

………………………………

Signature of Project Manager

Recommended by:

……………………….						………………………

Signature of Divisional Director					Signature of DDG (TO)

Approved by:

…………………………

DG/ CEO

Annexure 1

Estimated Recurrent Expenditure (excluding staff costs):

|  |  | Rs |
| --- | --- | --- |
| i | Components/ parts/ fabrication/ services | 100,000.00 |
| ii | Transport/ subsistence | 300,000.00 |
| iii | Accommodation | 200,000.00 |
| iv | Payments to external resource personnel | 100,000.00 |
| v | Equipment usage charges (major equipment) |  |
| vi | Miscellaneous/ contingencies/ | 50,000.00 |
| vii. | Other (Research paper publications fees) | 500000.00 |
|  |  | 800,000.00 |

Estimation cost for the project

|  |  | Rs |
| --- | --- | --- |
| 1 | Recurrent Expenditure (excluding staff costs) | 800,000.00 |
| 2 | Staff costs | 1260,000.00 |
| 3 | Indirect Costs |  |
| 4 | Equipment usage charges (general) |  |
|  | Utilities and other overheads |  |
|  | Total amount | 2060,000.00 |